## Sheet1
Milestone Planning of Project ToDo List
Sl. No. | Project Milestone | Exp Start Date | Expected Completion Date | Actual Completion Date
1 | Project planning | 09/10/2019 | 09/10/2019 | 09/10/2019
2 | Method for add project in file | 10/10/2019 | 10/10/2019 | 10/10/2019
3 | Method for display project on console | 10/10/2019 | 10/10/2019 | 10/10/2019
4 | Method for add task in file | 10/10/2019 | 10/10/2019 | 10/10/2019
5 | Method for display task on console | 10/10/2019 | 10/10/2019 | 10/10/2019
6 | Manual testing of above | 10/10/2019 | 10/10/2019 | 10/10/2019
7 | Push to GitHub | 10/10/2019 | 10/10/2019 | 10/10/2019
8 | Validation related to date and null entry in addTask() | 2019-10-11 | 2019-10-11 | 2019-10-24
9 | Auto project and task id generation | 2019-10-12 | 2019-10-12 | 2019-10-12
10 | Edit options for task | 2019-10-12 | 2019-10-14 | 2019-10-15
11 | Display task list with sorting : | 2019-10-16 | 2019-10-18 | 2019-10-18
a) Project-wise
b) Status-wise
c) Date-wise
d) Task Id-wise
12 | Remove Task from file | 2019-10-17 | 2019-10-17 | 2019-10-24
13 | Close and open task counting | 2019-10-21 | 2019-10-21 | 2019-10-23
14 | Junit testing | 2019-10-22 | 2019-10-22 | 2019-10-23
15 | Project Closure and upload to GitHub | 2019-10-24 | 2019-10-24 | 2019-10-24